## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Research on Python libraries for ANPR and ATCC | MUST HAVE | - | ALLU GANESH | 3- Completed
S1 | S1 | US-002 | Collect datasets for ANPR and ATCC | MUST HAVE | Kaggle, Hugging Face Account | ALLU GANESH | 3- Completed
S1 | S1 | US-003 | Research on YOLO models for ANPR and ATCC | MUST HAVE | - | ALLU GANESH | 3- Completed
S2 | S2 | US-001 | Data preprocessing for ANPR | MUST HAVE | OpenCV, PIL | ALLU GANESH | 3- Completed
S2 | S2 | US-002 | Labelling vehicles in dataset | SHOULD HAVE | - | ALLU GANESH | 3- Completed
S2 | S2 | US-003 | Training YOLO V9 model on dataset | MUST HAVE | Ultralytics | ALLU GANESH | 3- Completed
S2 | S2 | US-004 | Testing the model on test samples | MUST HAVE | OpenCV, YOLO | ALLU GANESH | 3- Completed
S2 | S2 | US-005 | Perform extraction of content from the detected regions | MUST HAVE | Groq | ALLU GANESH | 3- Completed
S2 | S2 | US-006 | Applying conditions on data extraction based on Traffic Violations | SHOULD HAVE | - | ALLU GANESH | 3- Completed
S3 | S3 | US-001 | Data preprocessing for ATCC | MUST HAVE | OpenCV | ALLU GANESH | 3- Completed
S3 | S3 | US-002 | Train the YOLO model on dataset | MUST HAVE | Ultralytics | ALLU GANESH | 3- Completed
S3 | S3 | US-003 | Classify and Count the vehicles in data based on classes | MUST HAVE | OpenCV | ALLU GANESH | 3- Completed
S3 | S3 | US-004 | Data visualization on related variables | COULD HAVE | Matplotlib, Seaborn | ALLU GANESH | 3- Completed
S4 | S4 | US-001 | Integrating ANPR and ATCC models | MUST HAVE | - | ALLU GANESH | 3- Completed
S4 | S4 | US-002 | Implement streamlit application for ANPR and ATCC | MUST HAVE | Streamlit | ALLU GANESH | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 39 | 3.5 | 4 | 5 | 5 | 5 | 4 | 3 | 3.5 | 1.5 | 1.5 | 0.5 | 0.5 | 1.5 | 1
SPRINT 1 BACKLOG
US-001 | TASK-001 | Research on suitable Python libraries for ANPR and ATCC | 2025-11-16 | 2025-11-17 | ALLU GANESH | Coding | 3- Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-001 | Explore datasets in open source websites | 2025-11-18 | 2025-11-20 | ALLU GANESH | Coding | 3- Completed | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-001 | Research on YOLO models | 2025-11-21 | 2025-11-22 | ALLU GANESH | Design | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-001 | TASK-001 | Load dataset into Google Colab Notebook | 2025-11-23 | 2025-11-25 | ALLU GANESH | Coding | 3- Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Splitting Train and Test data | 2025-11-25 | 2025-11-25 | ALLU GANESH | Coding | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-001 | Create label files for images in label folder | 2025-11-26 | 2025-11-28 | ALLU GANESH | Coding | 3- Completed | 4 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-001 | Import YOLO predefined model for object detection | 2025-11-28 | 2025-11-29 | ALLU GANESH | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-002 | Create coco for classes | 2025-11-30 | 2025-11-30 | ALLU GANESH | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-003 | Run and create YOLO model | 2025-12-01 | 2025-12-03 | ALLU GANESH | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-001 | Test the trained model in test data | 2025-12-04 | 2025-12-04 | ALLU GANESH | Build | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-001 | Generate Groq API from Groq website | 2025-12-05 | 2025-12-05 | ALLU GANESH | Others | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
US-005 | TASK-002 | Number plate's Text extraction | 2025-12-06 | 2025-12-06 | ALLU GANESH | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
US-006 | TASK-001 | Apply conditions like helmet detection, Mobile detection | 2025-12-07 | 2025-12-07 | ALLU GANESH | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
US-006 | TASK-002 | Apply condition for triple riding | 2025-12-08 | 2025-12-08 | ALLU GANESH | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
SPRINT 3 BACKLOG
US-001 | TASK-001 | Gather and load dataset into Google Colab Notebook | 2025-12-09 | 2025-12-14 | ALLU GANESH | Coding | 3- Completed | 6 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Split Train and Test data | 2025-12-14 | 2025-12-15 | ALLU GANESH | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-001 | Train YOLO model on data | 2025-12-16 | 2025-12-17 | ALLU GANESH | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-003 | TASK-001 | Detect and dislay vehicles using Computer Vision | 2025-12-18 | 2025-12-19 | ALLU GANESH | Unit Test | 3- Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
US-003 | TASK-002 | Apply confidence bar for adjustment | 2025-12-20 | 2025-12-20 | ALLU GANESH | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
US-004 | TASK-001 | Data visualization for vehicle classes and count | 2025-12-21 | 2025-12-22 | ALLU GANESH | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
SPRINT 4 BACKLOG
US-001 | TASK-001 | Integrate ANPR and ATCC models | 2025-12-23 | 2025-12-24 | ALLU GANESH | Coding | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-001 | Create streamlit app with integrated models | 2025-12-25 | 2025-12-28 | ALLU GANESH | Coding | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-002 | Deploy the model in streamlit cloud | 2025-12-29 | 2025-12-30 | ALLU GANESH | Others | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 7 | Unable to select proper dataset source for ANPR | Google meet to discuss about dataset sources
S2 | Day 12 | Problem with integrating large dataset | Finding alternative dataset
S2 | Day 16 | Difficulty in finding the suitable YOLO model | Group meet to select the model
S2 | Day 22 | Issue with extracting number plate content accurately | Used alternate library to extract text from number plate like Groq
S3 | Day 32 | Unable to choose video dataset for ATCC | Group meet to select proper source
S3 | Day 37 | Collection of test videos for ATCC | Discussed about collecting traffic videos individually
S4 | Day 45 | Difficulty in integrating two models in single app | Conducted a discussion with mentor
S4 | Day 53 | Better implementation of Presentation | Discussion with team and taken suggestion from mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-11-16 | 2025-11-22 | ALLU GANESH | Research on datasets and models | Using random dataset and trying to use it | Research on alternative sources | Gathered Dataset and chose YOLO model
2 | S2 | 2025-11-23 | 2025-12-08 | ALLU GANESH | Focus on model training and text extraction | Over training or Overfitting the model | Extraction of text from images | Implemented number plate recognition and extracted text
3 | S3 | 2025-12-09 | 2025-12-22 | ALLU GANESH | Implement vehicle classifier | Focusing on User Interface than classification | Data visualization on related data | Implemented vehicle counter and classifier
4 | S4 | 2025-12-23 | 2026-01-07 | ALLU GANESH | Integrate both models | Delaying integration of ANPR and ATCC | Streamlit app with models | Successfully integrated and created streamlit app